## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | User Registration and Login | This use case deals with the Login Homepage based on user credentials. The ‘user’ here shall be the operator of the system and will be keying in the user information into the system. | Task#1 | User needs to insert his/her UserId and Password to login in the homepage and then click on 'Submit'. | Critical |  | 28/3/19 | 28/3/19 | 5 |  | Done
| #2 | User Credential Authentication | This use case deals with the capture of user details. The ‘user’ here shall be the operator of the system and will be keying in the user details. | Task#2 | Clicking 'Submit' should validate the details of the user. | Critical |  | 28/3/19 | 29/3/19 | 11 |  | Done
|  |  |  | Task#3 | User failing to provide correct UserId or password be redirected to Login Page. | Medium |  | 29/3/19 | 29/3/19 | 1 |  | Done
| #3 | User Registration | This use case deals with the capture of user details. The ‘user’ here shall be the operator of the system and will be keying in the user details. | Task#4 | If the user is new, then perform user registration.User needs to fill Employee Id, First Name, Last Name, Age, Gender, Contact Number, Email Id, Password and Branch. | Medium |  | 29/3/19 | 29/3/19 | 3
|  |  |  | Task#5 | Upon saving the information in the database, redirect again to Login Page. | Medium |  | 29/3/19 | 30/3/19 | 3.5
|  |  |  | Task#6 | A registered user – is able click ‘Login’ link, after keying in ‘Employee Id’ & ‘Password’ field. | Medium |  | 29/3/19 | 30/3/19 | 0.5
| #4 | User Homepage | This use case deals with the homepage used by User. The ‘User’ here shall be the operator of the system and will be keying in the homepage details. | Task#7 | Admin’s on logging in should have Search Button,Update vehicle details Button and Logout Button. | Medium |  | 31/03/19 | 31/03/19 | 3 |  | Done
| #5 | Search vehicle | This use case deals with the Search Vehicle used by User. The ‘User’ here shall be the operator of the system and will be keying in the search details. | Task #8 | Admin on selecting the search criteria and clicking search, vechicle details- Branch, vehicle type,vehicle number,insurance expiry date, service due date should be listed from the database. | Critical |  | 31/03/19 | 2019-01-04 | 11 |  | Done
|  |  |  | Task #9 | If Expiry of Insurance or Service due falls in next 15 days from the Vehicle details listed, should be highlighted in red. | Medium |  | 2019-02-04 | 2019-02-04 | 10 |  | Done
|  |  |  | Task #10 | Admin on double clicking any of the listed vehicle number, should be redirected to Update page, or the user can also logout from this page. | Medium |  | 2019-03-04 | 2019-04-04 | 13 |  | Done
| #6 | Vehicle Updation | This use case deals with the updation of vehicle details by User. The ‘user’ here shall be the operator of the system and will be responsible for the updation of vehicle details. | Task #11 | Admin on clicking the Update Vehicle details button should be directed to Update details page | Medium |  | 2019-05-04 | 2019-06-04 | 9
|  |  |  | Task#12 | Update Details page should display all the fields- Vehicle No, vehicle type, Branch, insurance type, insurance expiry date, last Serviced Date, Service due date | Critical |  | 2019-06-04 | 2019-06-04 | 2 |  | Done
|  |  |  | Task #13 | Upon saving the information in the database, redirect again to Update Page and it also consists of Logout Button. | Medium |  | 2019-06-04 | 2019-06-04 | 2 |  | Done | We have taken userId as the primary key and assigned userType as 'U' for user.
| #7 | Vehicle Insertion | This use case deals with the addition of new vehicle entry. The ‘user’ here shall be the operator of the system and will be responsible for the insertion of the new vehicle. | Task#14 | Admin should have access to create a new vehicle details entry | Medium |  | 2019-06-04 | 2019-08-04 | 15 |  | Done
|  |  |  | Task#15 | Admin should have access to update details of existing vehicle details. | Medium |  | 2019-08-04 | 2019-09-04 | 15 |  | Done
|  |  |  | Task#12 | Admin on entering existing Vehicle Number, the rest of the details should be loaded in the respective labels from database.
|  |  |  | Task#13 | On creating/updating the vehicle details, each fields should be validated and appropriate error messages should be thrown. | Critical |  | 2019-10-04 | 2019-10-04 | 2 |  | Done
|  |  |  | Task#14 | Admin on logging in should have Search vehicle details Button and Logout Button. | Medium |  | 2019-10-04 | 2019-10-04 | 3 |  | Done
|  |  |  | Task#15 | Admin on clicking the Search Vehicle details button should be directed to Search details page | Medium |  | 2019-10-04 | 2019-11-04 | 5 |  | Done
| #8 | Notify User | This use case deals with the ability to generates the mail that should be run fortnightly to trigger Email notification to admin to notify – Expiry of Insurance in next 15 days or Service due in next 15 months. | Task#16 | Batch job should be run fortnightly to trigger Email notification to admin to notify –Expiry of Insurance in next 15 days or Service due in next 15 months | Critical |  | 2019-11-04 | 2019-11-04 | 2 |  | Done